## Slide 1: Managing the Test Scripting Process

## Slide 2: Introduction
This session will look at ways of effectively managing the test scripting process
It will stress that script writing must also back to agreed testable requirements
And also look at ways of ensuring that test scripts produced support effective test execution

## Slide 3: Purpose of Test Scripting
Test scripting brings the gap between requirements gathering and test execution
It is the method by which order and structure is imposed on what would otherwise be just adhoc checking and review of the delivered software

## Slide 4: Managing the Test Scripting Process
As a Test Manager your role during the process is quite simple
    Oversee an efficient and focussed conversion of requirements into tests
    Prevent test scripting becoming bogged down
    Prevent avoidable gaps in coverage occurring
    Ensure that test scripts support rather than hinder test execution

## Slide 5: Oversee efficient and focussed conversion of requirements into tests
Don’t let your team get lost in the detail of scripting
1
Stay aware of the bigger picture
2
Focus on the areas of highest criticality first
3

## Slide 6: Oversee efficient and focussed conversion of requirements into tests
Prepare a requirements map/matrix showing
Source of all requirements
Criticality of each source and area
The scripting status of each source
Use this map to drive your team’s scripting priorities

## Slide 7: Requirements Map Example

## Slide 8: Prevent test scripting becoming bogged down
If scripting an area starts proving problematic
Rotate scripting responsibilities amongst your team
Helps stop testers becoming stale or jaded
Fresh pair of eyes may see a new way around the issues
If there are issues with the source requirements
Raise the issues and move onto another area
Script in waves, increasing depth of coverage each time
Means you quickly have SOME coverage in all areas

## Slide 9: Prevent avoidable gaps in coverage occurring
Ensure
Ensure your team prepare requirement traceability matrices for each area they script
Check
Check these matrices for
Requirements with no tests
Tests which do not link back to requirements
Pay
Pay particular attention where there is a many to many relationship between requirements and tests

## Slide 10: Prevent avoidable gaps in coverage occurring
Spot check a sample of test in detail but leave the majority to other members of your team
Important to remember
    Some coverage is not the same as full coverage
In complex areas ask testers to explain how they have ensured the requirements are covered in full
    Check for flaws in their logic/approach

## Slide 11: Test scripts support rather than hinder test execution
Ensure
Ensure that test scripts are
Clear
Short
Precise
Remember
Remember: Every test should tell you something new about the application
Avoid
Avoid long scripts with many separate steps where possible as
They often end up failing halfway through
They are not easy to split across multiple testers

## Slide 12: If there are gaps or issues with requirements docs. when scripting begins
Log each gap or issue as a defect
Resolve via your standard defect management process
If the issue is not resolved by the time execution starts, should be raised as a project risk
Ensures that gaps and issues receive plenty of attention

## Slide 13: Reporting Test Scripting Progress
Always Report in terms of requirements coverage and not numbers of scripts written
Show how many requirements
    Are fully scripted
    Are partially scripted
    Have no scripts at all
Classify progress in terms of the criticality of each area of the delivery
List issues raised against requirements and their status
Make it clear when issues block significant areas of functionality

## Slide 14: Forecasting
Just as we need to allow for Potential Requirements when measuring requirements coverage
So we also need to allow for Potential testcases when measuring scripting progress

## Slide 15: How do we do this ?
For gaps within a functional area
Work out average number of tests per requirement in other areas to date
Apply this factor to unscripted area to give a notional number of tests to be written in order to fully test that area
Where an entire area has no requirements
Use the figures for an area you believe to be similar in size and complexity
Apply average number of tests per requirement to this figure

## Slide 16: A Worked Example
(Notional Figures in RED) |  |  |  |  |  |  | 
Area | assumption | Total Reqs. | Requirements Fully Covered | actual tests | tests per req | notional tests | total tests required
A | use average for that area | 45 | 25 | 42 | 1.68 | 34 | 76
B |  | 12 | 12 | 27 | 2.25 | 0 | 27
C | use average for that area | 3 | 2 | 6 | 3 | 3 | 9
D | use average for that area | 62 | 60 | 112 | 1.8667 | 4 | 116
E | same as B | 12 | 0 | 0 |  | 27 | 27
F |  | 11 | 11 | 0 | 0 | 110 | 110
Totals |  | 145 | 110 | 187 | 1.7 | 187 | 364
Area | assumption | Total Reqs. | Requirements Fully Covered | actual tests | tests per req | notional tests | total tests required

## Slide 17: How do we use this data?
Make Identifying gaps in script coverage simpler
Also can compare actual with expected progress as follows
Compare what % of this figure has already been scripted and compare this with the time elapsed
45% of total tests scripted, 60% of allotted time elapsed. We are behind schedule
65% of total tests scripted, 50% of allotted time elapsed. We are ahead of schedule

## Slide 18: Caution…..
Actual numbers of test unlikely to be the ever exactly the same as those returned by your calculations
Not all tests take the same time to script
Different areas must be tested in different ways
Etc.
Still much better than ignoring unscripted areas altogether in your reports!

## Slide 19: What if time is running out?
To mitigate the impact of lack of time and/or resources during this phase the following order of priority should be followed wherever possible
  Aim for at some high level coverage in each area first
    These will form the basis for rattle testing each new build and for your regression pack
  Then write the detailed cases in each area based on business criticality
    If time is really short write the positive tests only but make a note to come back to complete the negative tests for testing against a later build

## Slide 20: What if time is running out?
This is ensure that whatever scripts you prepare will test the most important elements in each delivery
and at least find the biggest and most obvious defects in each area

## Slide 21: Conclusion
This session has looked at common issues which may hold back effective test scripting
And suggested ways in which the process can be more effectively managed
The goal of test scripting is to allow effective test execution
This is the phase in the process that we will look at next